| ACO Agent — Road to Production | Vertiv Talent Acquisition Compliance Automation |
| --- | --- |
| From proof-of-concept to operationalized compliance platform. A sprint plan for HR, Legal, and Engineering. | Sri Kavuru ¦ June 2026 DRAFT — Internal Use Only |

1. The Problem

Vertiv posts hundreds of job descriptions per year across 130+ countries. Each posting must comply with federal employment law (Title VII, ADA, ADEA, ITAR), state-specific pay transparency statutes (now 17 states and growing), and internal brand standards. Today, compliance depends on:

Manual recruiter review against a mental checklist that changes with every new state law

Legal sending policy PDFs (like Pay Transparency V14) that must be read, understood, and manually applied

No systematic way to verify compliance before a posting goes live

No audit trail proving what was checked, when, and by whom

The risk is real: a single missing pay range in Colorado or a stray "young professional" in a posting creates direct legal exposure. The gap between "policy published" and "policy enforced" is where violations happen.

2. The Proof Point — V14 Same-Day Enforcement

On June 25, 2026, Legal distributed the Pay Transparency Language V14 policy update — expanding mandatory pay transparency from 8 states to 17. Within the same day:

| Policy received | Pay Transparency V14 document distributed by Legal |
| --- | --- |
| Rules updated | 4 new compliance rules added, 2 existing rules expanded to cover 17 states |
| Engine deployed | Updated audit engine pushed to production — zero downtime |
| Enforcement live | Every JD submitted from that moment forward is checked against V14 requirements |

This is the model: Legal publishes policy → Engineering encodes rules → recruiters see enforcement immediately. No training sessions, no lag, no "I didn't get the memo." The V14 update proves it works. The question is: how do we operationalize it?

3. The Ongoing Workflow — HR, Legal, and Engineering

ACO Agent creates a structured handoff between three teams. Each owns a clear lane:

| Team | Role | What They Do |
| --- | --- | --- |
| Legal / Compliance | Policy Authority | Publishes compliance policy updates (e.g. V14). Defines what rules exist, what severity they carry, and what legal citations apply. Reviews CRITICAL/HIGH rule definitions before they go live. |
| Engineering | Rule Encoder | Translates Legal's policy into machine-readable rules in rules.json. No code changes needed for most updates — just JSON. Runs tests, deploys. Maintains the audit engine and semantic matching. |
| HR / Recruiting | Decision Authority | Submits JDs for audit. Reviews findings. Owns the publish decision. ACO never blocks autonomously — it surfaces issues. Every audit certificate says "decision_authority: HUMAN_RECRUITER." |

Policy Update Lifecycle

| 1 Legal publishes policy update | 2 Engineering adds rules to JSON | 3 Automated tests validate rules | 4 Deploy to production | 5 Recruiters see enforcement |
| --- | --- | --- | --- | --- |

Turnaround target: same-day for keyword/regex rules, 1-2 days for semantic rules requiring threshold tuning.

4. Current State — Built vs. Remaining

| Capability | Status | Notes |
| --- | --- | --- |
| Rule Engine (5 match types) | BUILT | Semantic, keyword, keyword_list, regex, computed |
| 24 Compliance Rules | BUILT | Across 5 categories, including V14 pay transparency |
| Audit Certificate Generation | BUILT | Structured JSON with severity, citations, remediation |
| Recruiter Web UI | BUILT | 5 tabs: Audit, Batch Scrape, Rules, What's New, Reporting |
| ORC Webhook Integration | BUILT | Auto-audit on requisition draft save in Oracle Recruiting Cloud |
| CosmosDB Persistence | BUILT | 7-year TTL, partitioned by region |
| Compliance Dashboard & Trends | NOT STARTED | Track failure rates by rule, recruiter, department over time |
| Auto-Remediation Mode | NOT STARTED | One-click boilerplate insert for CRITICAL missing blocks |
| Recruiter Notifications | NOT STARTED | Slack/Teams alert on BLOCKED certificate |
| OFCCP Audit Package Export | NOT STARTED | PDF per requisition for 7-year legal hold |

5. Sprint Plan — 3 Sprints to Production-Ready v2

Each sprint is scoped to 2 weeks. Deliverables are ordered by business impact and dependency chain.

Sprint 1: Foundation & Visibility (Weeks 1-2)

Goal: Give leadership and recruiters visibility into compliance trends. Prove the data is accumulating and actionable.

| Deliverable | Owner | Details |
| --- | --- | --- |
| Compliance Dashboard | Engineering | Failure rate by rule, by recruiter, by department. Trend lines over time. Top 5 most-violated rules. Filterable by date range and region. |
| Audit History Search | Engineering | Search past audits by req number, recruiter, date, or status. Currently limited to session — needs CosmosDB query integration. |
| Legal Review of All 24 Rules | Legal | Formal sign-off on every rule_id, severity level, and failure_message. Document any adjustments. This is the compliance baseline. |
| Semantic Threshold Tuning | Engineering + HR | Run the 24 rules against 50+ real Vertiv JDs. Identify false positives/negatives. Adjust thresholds per rule. Document results for legal defensibility. |

Sprint 2: Automation & Workflow (Weeks 3-4)

Goal: Reduce friction. Make compliance the path of least resistance, not an extra step.

| Deliverable | Owner | Details |
| --- | --- | --- |
| Auto-Remediation Mode | Engineering | For CRITICAL missing blocks (EEO, ADA, work auth, core principals), offer one-click insert of Legal-approved boilerplate. Recruiter approves the insert — ACO never writes autonomously. |
| Recruiter Notifications | Engineering | Slack or Teams webhook when a BLOCKED certificate is issued. Includes direct link to the finding and remediation template. Configurable per recruiter or team. |
| ORC Full Integration Test | Engineering + HR | End-to-end test: create a draft requisition in ORC → webhook fires → audit runs → certificate written back. Validate with 10 real requisitions across different regions. |
| Rule Update SOP Document | Legal + Engineering | Written standard operating procedure: how Legal requests a rule change, how Engineering implements it, how it gets tested and deployed. Includes rollback procedure. |

Sprint 3: Audit Trail & Legal Hold (Weeks 5-6)

Goal: Make the system OFCCP-audit-ready. Every posting has a defensible compliance record.

| Deliverable | Owner | Details |
| --- | --- | --- |
| OFCCP Audit Package Export | Engineering | PDF per requisition: original JD, audit certificate, all findings, recruiter sign-off timestamp, publication date. One-click export from the dashboard. |
| Recruiter Sign-Off Workflow | Engineering + HR | Explicit "I have reviewed these findings" acknowledgment before publishing. Captured in the audit certificate with timestamp and recruiter identity. |
| 7-Year Retention Validation | Engineering + Legal | Verify CosmosDB TTL policy, backup strategy, and data retrieval process. Simulate an OFCCP records request end-to-end. |
| Production Readiness Review | All Teams | Security review, access controls, PII handling, disaster recovery. Final sign-off for company-wide rollout. |

6. The Ask

To execute this plan, we need:

| Need | Why |
| --- | --- |
| Legal sign-off on current 24 rules | Every rule_id, severity, and failure_message needs formal approval before company-wide rollout. This is the compliance baseline we'll defend in an audit. |
| 50+ real JDs for threshold tuning | We need recent, actual Vertiv postings across regions and job families to calibrate semantic matching and eliminate false positives. |
| ORC sandbox access | Full integration testing requires a non-production ORC environment to validate the webhook end-to-end without affecting live requisitions. |
| Slack/Teams webhook approval | IT needs to approve an incoming webhook for BLOCKED certificate notifications. Standard security review. |
| Executive sponsor for company-wide rollout | When Sprint 3 completes, we need someone to champion the transition from "pilot tool" to "standard process" for all U.S. postings. |

Timeline Summary

|  | Sprint 1 (Wk 1-2) | Sprint 2 (Wk 3-4) | Sprint 3 (Wk 5-6) |
| --- | --- | --- | --- |
| Engineering | Dashboard, history search, threshold tuning | Auto-remediation, notifications, ORC test | PDF export, sign-off workflow, retention test |
| Legal | Rule review & sign-off | Rule update SOP | 7-year retention validation, prod review |
| HR / Recruiting | Provide JDs for tuning, validate findings | ORC integration test, notification setup | Sign-off workflow UAT, rollout prep |

ACO Agent  |  Decision support only — all publish decisions are human-owned  |  Vertiv Talent Acquisition  |  DRAFT